LWCF/Section 6(f) Conversion Process

| Contact OPRD to determine whether or not proposed activity on a site protected by Section 6(f)(3) of the LWCF Act requires official NPS approval. | Project Sponsor |
| --- | --- |
| Consult with NPS to confirm Section 6(f)(3) park boundary (from previously funded LWCF projects and NPS grant files), whether the proposed activity is within NPS’ jurisdiction, and whether the proposed activity requires further NPS involvement. | OPRD |
| Coordination meeting with OPRD and NPS to discuss size and type of conversion and next steps. (Agreement on conversion footprint must take place prior to proceeding with NEPA, NHPA, appraisals, etc.). | OPRD/ Project Sponsor/ NPS |
| Identify potential replacement property; obtain agreement by OPRD and NPS | Sponsor |
| Develop general concept plan for replacement property, clarifying which elements will be developed to resolve the conversion and which are planned for future phases. | Sponsor |
| NHPA - Initiate Section 106 consultation. - Obtain cultural resource surveys for conversion and replacement, as needed. - Issue determination of effect. - Execute agreement document as needed. | OPRD / NPS / Sponsor |
| Appraisals - Appraisal for converted property (should be completed first to determine fair market value of converted property and to determine how much replacement property will be required). - Appraisal for replacement property. The fair market value of the replacement property must be of equal or great in value as the converted property. - Appraisals for converted and replacement properties must comply with the Uniform Appraisal Standards for Federal Land Acquisitions (“yellow book”). - Appraisals must be reviewed by an independent appraisal reviewer. - Appraisals must be submitted to OPRD. They may also be reviewed by Department of the Interior if there are concerns, controversy, or unusual circumstances. | Project Sponsor/Appraiser |
| NEPA - Fill out the screening form portion of the PDESF, one for the conversion, and one for each proposed replacement property. - If the proposal will meet the criteria for a Categorical Exclusion, fill out the rest of the PDESF - If the proposal will not qualify for a CatEx (this is typical) write an Environmental Assessment focusing on those areas identified in the screening form as having adverse or unknown impacts. NPS has a template available for this. - Submit draft to OPRD and NPS. - Once draft is approved, release for public comment for a minimum of 30 days. - Respond to public comments. - Submit document, public comments, and responses to OPRD. | Project Sponsor |
| Maps – develop and submit to ORPD the following: - Map depicting the conversion footprint in context with the remaining 6(f) boundary, if any. - New 6(f) map for original park, if the conversion is only a partial conversion. - Location map showing the relative location of the conversion and replacement(s) to one another. - New 6(f) map for the replacement(s) | Project Sponsor |
| Formal transmittal letter to OPRD requesting approval of conversion and replacement property. - NEPA documents - NHPA documents - Appraisals - Maps | Project Sponsor |
| OPRD prepares and submits conversion request for submittal to NPS. - Transmittal Letter from SLO to NPS requesting approval of conversion - 2 signed amendments (signed by SLO or ASLO) - SF424 - NEPA documents - NHPA documents - Proposed development and schedule for replacement property - Maps – official 6(f) maps must be signed by SLO or ASLO - Appraisal summary of converted and replacement property from appraisals with appraisal review | OPRD |
| Review and approval of conversion request. Sign and return State/NPS Amendment to OPRD. | NPS |
| Prepare and submits State/Local Amendment to project sponsor. | OPRD |
| Signs and returns State/Local Amendment to OPRD | Project Sponsor |
| SLO signs and returns State/Local Amendment to project sponsor. | OPRD |

OPRD = Grant Program Coordinator, Recreation Grants Division – Michele Scalise

Project Sponsor = Grant recipient/responsible party (City, County, District, Metro, State Agency)

NPS = Program Officer, Pacific West Region